## Preamble
Club COVID-19 Risk Registry
Context
This risk registry was created following the emergence of the COVID-19 global pandemic. The risks summarized in this Registry are the HIGH LEVEL risks identified by "Your Club" operations team. This document should be treated as CONFIDENTIAL which means that it should not be shared with anyone outside of the organization [club, or club board?].
Background
Of note, this comprehensive approach to risk management takes into account the organization’s values and in so doing empowers the participants to consider ways to not only minimize risks, but also seek out new opportunities.
Our Vision
Your Clubs Vision
Our Mission
Your Clubs mission statement
Our Values
your Clubs values & statements
Probability (P) * Use the numbers to score each Risk Probability
1- Rare
2- Unlikely – less likely to happen than not
3- Possible – just as likely to happen as not
4- Likely – more likely to happen than not
5- Almost certain – sure to happen
Consequence (C)
1- Insignificant
2- Minor – will have an impact on the achievement of the objective that can be dealt with through internal adjustments
3- Moderate – will have an impact on some aspect of the achievement of the objective that will require changes to strategy or program delivery that may cause a delay/ increase in cost/ time
4- Serious – will significantly impact the achievement of the objective that will likely require additional time, resources, costs, and strategic discussion
5- Catastrophic’ – will have a debilitating impact on the achievement of the objective; staff and board are likely to devote full time resources to manage the situation
Risk Management Principles: The International Standard Organization (ISO 31000:2009E) principles that were used to develop the process for this analysis:
ü Risk management creates and protects value
ü Risk management is an integral part of all organizational processes
ü Risk management is part of decision making
ü Risk management explicitly addresses uncertainty
ü Risk management is systematic, structures and timely
ü Risk management is based on the best available information
ü Risk management is tailored
ü Risk management takes into account human and cultural factors into account
ü Risk management is transparent and inclusive
ü Risk management is dynamic, iterative and responsive to change
ü Risk management facilitates continual improvement of the organization
Existing measures: These are the current strategies, practices, procedures, programs and initiatives that the organization already has in place to reduce the likelihood of the risk occurring or reduces its consequences should it occur.
Possible measures: These are the ideas for new strategies, practices, procedures, programs or initiatives that were generated during the risk management workshop.
Communications: Risk communication helps organizations to understand and communicate what its risk tolerance is, thus potentially resulting in new behaviours and decisions. To be effective, every risk management measure requires a communications component that is captured in the risk registry. While risk communications alone does not address all risks, effective communications are essential aspects of all risk management measures. In some cases, risk communication can help to prevent a risk from occurring.
Commitments: These are the agreed-upon actions that the organization will pursue to address an area of risk.
Monitoring: The person or group responsible for assigning or taken responsibility for the management of the risk.
Note on A20: Curtis: Do we need the time scale to this?

## Club Membership
"Your Club Name Here" Risk Registry
Step 1: Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Response Strategy | Step 4: Risk Response Planning |  |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Assigned To | Target Due Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5-Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5- Catastrophic | Low (1-2), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Club Membership | Sharp decrease in league participation due to economic downturn, fear of virus transmission. | Provincial Restrictions/Guidelines | Decreased revenue, club may opearte with the expectation of a loss for the season or may need to close | 4- Likely | 4 (major)- 5 (Catasrophic) | High (4-5) | Mitigate | Initial Survey to membership to find out the level of comfort to return to play.
[9 empty] | Create a 4 scenario plan for the fall |  |  |  |  | 1. Limited Restricton Season, 2. Under 50 People Season, 3. Disrupted Season, 4. No season
Consider online fundraising initiatives for contactless revenue (50/50).
Continue to access resources and networking opportunities through Curl BC
Access programming from Curl BC
Increased marketing efforts
Contact Sponsors and work on agreements with new innovative deliverables
[9 empty] | Map out the facility to see how to flow participants into/out of the ice/lounge/building with current physical distancing restrictions & staying under 50 people at one time |  |  |  |  | How many people can we safely have with the 2 meter restrictions?
| Club Membership | Decrease in social activities due to virus transmission fears/reality | Provincial Restrictions/Guidelines | decreased club revenue/ interest in participating | 4- LIkely | 4- Major | High (4-4) | Mitigate | Include strategies from food/beverage industry return to opening procedures to minimize risk
Physical Distance mapping of the lounge/flow of people if able to operate amenities (kitchen and/or bar)
[9 empty] | survey members on other opportunities the club can offer |  |  |  |  | Off ice low impact activities for members (ie: Yoga; table top curling, board games)
| Club Membership | Decreased program/course revenue due to downturn in economy |  | decreased general revenue | 3- possibly | 3- Moderate | Medium | Accept | invest in adjusted programming |  |  |  |  | How to offer coaching clinics with physical distancing.
[9 empty] | plan for increased demand when courses reopen |  |  |  |  | Providing training for volunteers/coaches to keep them updated, engaged, and ready to mobilize as things open up.
Adjust any program models
recruit partners/sponsors to reduce user fees

## Communication
"Your Club Name Here" Risk Registry
Step 1 Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Strategy Response | Step 4: Risk Response Planning |  |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Assigned To | Action Target Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5- Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5-Catastrophic | Low (1-2), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Communication | Lack of ability to reach key stakeholders due to layoffs/personal circumstances related to COVID-19 impacts |  | key communications may not reach key stakeholders | 4- Likely | 4- Major | High (4-4) | accept | Personal calls to every member club/ key stakeholder to update contact information
delay or postpone any major announcements/impacts
| Communication | Virtual AGM | Provincial Restrictions/Guidelines | Unable to host AGM due to lack of quorum | 3- Possible | 4- Major | Medium (3-4) | Enhance | Use all media platforms to commmunicate virtual AGM or AGM date change

## Financial
"Your Club Name Here" Risk Registry
Step 1 Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Strategy Response | Step 4: Risk Response Planning |  |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Assigned To | Action Target Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5- Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5-Catastrophic | Low (1-2), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Financial | Curl BC Affiliation Fees | Curl BC updates | May impact club fees | 3- Possible | 3- Moderate | Medium (3-3) | Accept, Exploit, Share, Enhance | Communication with Curl BC
| Financial | Decreased Sponsorship | Economic Downturn | Less Revenue Support | 4- Likely | 4- Major | High (4-4) | Mitigate, Enhance | Reach out to Sponsors
Target For In-Kind sponsorship.
Target sponsors with less impact to business during the pandemic.
revisit agreements and potentially modify to reflect changing reality
Seek out new angles/opportunities
| Financial | Decreased grant/Gaming revenue | Declined applications. | May not be able to provide usual supports to programs | 3- ossible | 4- Major | medium | Mitigate, Accept | Re-evaluate Gaming funds spending plan.
|  |  |  | Base funding will be status quo. |  |  |  |  | Re-evaluate specific programs to ensure long-term viability (or discontinue based on other strategic objectives)
Pursue other alternative funding sources (look to other non-traditional sport/industry reactions- e.g. major or star power event, province-wide 50/50 or other raffles/lotteries, etc.)

## Operations
"Your Club Name Here" Risk Registry
Step 1 Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Strategy Response | Step 4: Risk Response Planning |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Action Target Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5- Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5-Catastrophic | Low (1-2), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Operations | Municipalities may not allow for curling to return. |  | loss of curling in the community | 2- Unlikely | 5- Catastrophic | Medium | Mitigate | Stay Connected with City/Municipal partners
| Operations | Plant Failure | Aging Equimpent breaks (needs replacement) | Loss of Curling until equipment can be installed | 3- Possible | 4-Major | Medium | Avoidance | Capital Planning and Fundraising in place
| Operations | Decreased volunteer base due to downturn in economy | Lack of volunteers signing-up for committees/ events/ etc | Lack of capacity to run club/program/sevents | 3- Possible | 3- Moderate | Medium (3-3) | Avoidance, Exploit Opportunities, Share Benefits | Communicate with Key volunteers
ensure sound volunteer management strategies are in place (e.g. recruitment, training, recognition, etc.)
Survey membership for new volunteers.
Ask volunteers what support/ resources they need.
Provide Volunteer Training
| Operations | League play with 50 person limit | Provincial Restrictions/Guidelines | opearting at partial capacity | 3- Likely | 3- Moderate | Medium (3-3) | Accept, Enhance | Brainstorm how to maximize the 50 people in the club.

## Staff and Board
"Your Club Name Here" Risk Registry
Step 1 Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Strategy Response | Step 4: Risk Response Planning |  |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Assigned To | Action Target Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5- Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5-Catastrophic | Low (1-3), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Club Employees | Payroll capacity/ employee layoffs | [6 empty] | Development & Transition Steps
|  | 1. Key Senior Leaders Roles (General Managers) | Layoff GM | Loss of organizational knowledge & leadership | 2- Unlikely | 4- Major | Medium (2-4) | Mitigate | Secure Position and Funding to maintain your GM |  |  |  |  | Have an organizational chart outlining all of the roles and person(s) responsible for the role(s). Identify what "action" you would take in the event you cannot maintain a manager (can this role be covered by an interim volunteer) what other options are available?
|  | 2. Key Operational Roles (Head Ice Techs/Chefs) | Lack of Business | Loss of ice staff/kitchen staff | 2- Unlikely | 4- Major | Medium (2-4) | Mitigate | secure position to have ice tech ready for return to play. |  |  |  |  | Evaluate the risk of losing these key operating personnel. Do you have anyone internal to take over the position? Or would you have to hire externally? Is this something that can be covered by volunteers on a short-term until a long-term solution can be provided.
|  | 3.Potential Internal Successors (Admin Staff/Support staff) | Interim Layoffs which last over extended period. (3-6 months( | loss of upcoming successors | 3- Possible | 2- Minor | Low (3-2) | Accept | have a development plan/transition plan for staff to move into other roles |  |  |  |  | Create/Use an On-Boarding checklist that outlines the major steps to be addressed after hiring a candidate.
|  | Staff may burn out/leave the organization for more stable employment | Lack of full time work
| Board Governance | Loss of key board members | people in key positions contract the virus | having to fill key positions during a crisis | 2- possible | 3- Moderate | Low (2-3) | Mitigate | Ensure board members have support/resources to continue in their roll.
|  |  |  | Depending on timing/duration/who, this could lead to a temporary delay/halt to some operations |  |  |  |  | maintain work from home policy during the pandemic
|  |  |  | Most likely to impact AGM |  |  |  |  | may need to assign back-up committee members
Create/Enhance Emergency Succession Plan
Ensure Vice Chair is prepared to chair AGM and first new board meeting
|  | Board Recruitment decreases | People less willing to participate/volunteer their time. | Creates uncertainty for the organization | 2- Possible | 3- moderate to 4- major | Medium (2-4) |  | Target new board members to compliment existing skill sets and future needs of the organization
May create mismatched/narrow Board skill sets
|  | In-person AGM cancelled | Provincial Restrictions/Guidelines | will require use of technology to host without physically gathering | 3- Possible | 2- Minor | Low (3-2) | Enhance | rehearse/test virtual AGM procedures
|  |  |  | may be more difficult to ensure quorum |  |  |  |  | communications plan to attract voting members
attend other AGM's for best tips/practices

## Safe Sport
"Your Club Name Here" Risk Registry
Step 1 Risk Identification |  |  |  |  | Step 2: Risk Assessment |  |  | Step 3: Strategy Response | Step 4: Risk Response Planning |  |  |  | Step 5: Monitor Actions | Notes
Rank | Risk Category | Description of Risk Event | Risk Event Trigger | Potential Impact if Risk Occurs | Probability of Risk Happening | Consequences of the Risk | Risk Score | Avoidance, Transfer, Mitigate | Action Plan/Contingency Plan | Assigned To | Action Target Date | Date Achieved | Status
[5 empty] | 1- Rare, 2- Unlikely, 3- Possible, 4- Likely, 5- Almost Certain | 1- Insignificant, 2- Minor, 3- Moderate, 4- Major, 5-Catastrophic | Low (1-2), Medium (3-4), High (4-5) | Accept, Exploit, Share, Enhance
| Physical Environment | Are there spaces and locations in your organization that provide opportunities for time alone with a child or vulnerable adult? | [11 empty] | Factors that increase physical safety:
|  | Have you examined the physical environment and ways in which physical, sexual, emotional abuse can occur unnoticed? | [11 empty] | High visibility in all areas, privacy in bathrooms (for school aged children and adults), separate sleeping quarters for adults/children, adequeate lighting.
Are the spaces for children/adults designed to be open, visible, and monitored?
Is the space operating at capacity?
Do spaces provide access to individuals not involved in your programs (public areas/access?)
Other
| Programs, Activities, and Services | Does your organization fully understand all of the programs and services it offers to children and how they are run? | [11 empty] | Factors that increase safety include:
|  | Have risk assessments been performed on each program/service/activity/area? (Overnight trips, coaching, etc) | [11 empty] | Employees/Volunteers are trained and aware. High adult-to-child rations, monitoring and supervision of employees/volunteers, high parental involvement, limited one-on-one activities, limited physical contact.
Are there particular activities where children are isolated or with less supervision (people's homes, vehicle transportation, dressing rooms, etc)?
Do you run any programs that include changing into athletic gear? Toileting?
Do your programs include transportation services?
Are programs/service/activity risk assessments regularly completed and reviewed?
Does the program involve potential phsyical restraint of the child/adult by employees or volunteers?
Other?
| Organziational Culture | Does your organization prioritize the issue of child protection/participant protection? | [11 empty] | Factors that increase organizational safety:
|  | Do employees/volunteers have a good understanding of child sexual abuse and disclosure? And/or Abuse/Harrassment | [11 empty] | Organization embraces change, open door policies, transparency and accountability, positive attitudes and beliefs, low employee/volunteer turnover.
Is your organization transparent and/or open to outside ideas?
Does your organization have an open door policy for addressing concerns? Is there excessive secrecy and discussion behind closed doors?
Are parents welcome to observe or participate in activities?
Are sensitive issues (sexual abuse, inappropriate adult/child interaction, etc) open for discussions? Are employees/volunteers included in the discussion?
Are employees/volunteers motivated and committed to improving child/participant safety?
Policies and Procedures, does your organization have established child protection/participant protection policies and procedures in the following areas: | [13 empty] | Facators that increase safety: codes of conduct, child protection policies and procedures, participant protection policies and procedures (harrassment policies, equity & access policies), effective screening and hiring practices, supervision of employees/volunteers, clear reporting procedures.
Education and Awareness
Hiring Practices
Orientation and supervision (guidelines for supervising employees/volunteers)
Reporting and documenting suspicions of child sexual abuse.
Reporting and documenting inappropriate conduct by an employee/volunteer
Suspension and dismissal
Accountability and Confidentiality
Programs, services, and activities
Policies and Procedures |  | Are child protection/participant protection policies and procedures clearly communicated to all employees/volunteers?
Does your organization have a code of conduct that outlines appropriate employee/volunteer behaviour toward children?